## Approval Workflow
Content Approval Workflow
Partnership Name: |  | Creator Name: |  | Campaign Dates: |  | Revision Rounds Included:
Fill in the header cells before your kickoff call. Orange cells are inputs to determine during call.
Stage | Reviewer / Role | What They're Evaluating | Turnaround (Business Days) | Approval Signal | Revision Trigger | Notes / Escalation
Stage 1 — Draft Submitted by Creator | Creator | Internal only — confirm receipt | 1 day | Confirmation sent via designated channel | N/A | Channel for submission must be decided at kickoff. One channel. Don't change it mid-project.
Stage 2 — Marketing Lead Review |  | Brand alignment, messaging guardrails, key message inclusion, FTC disclosure language | 2 days | Written confirmation — 'approved for next stage' or revision notes — via designated channel | Factual error, missing required element, off-message claim, disclosure missing | If no response in 2 days, escalate to [backup contact — enter at kickoff]
Stage 3 — Legal / Compliance Review |  | FTC compliance, claim substantiation, regulated language, contractual term adherence | 3 days (build for 3, not 2) | Written sign-off. Logged in tracking document. | Unsubstantiated claim, required disclosure absent, prohibited language present | Legal review cannot be skipped. If timeline is at risk, flag to campaign owner — not to the creator.
Stage 4 — Executive Review |  | Strategic alignment, brand positioning, messaging sensitivity | 1–2 days | Email or Slack confirmation | Strategic misalignment, message conflicts with active campaigns or pending announcements | Most common timeline killer. Flag to marketing lead if executive is unresponsive. Do not tell the creator this stage is the holdup.
Stage 5 — Final Approval Issued to Creator | Marketing Lead [name] | Confirm all stages complete. Communicate final approval. | 1 day after all reviews complete | Explicit written approval sent to creator. Date logged in Deliverables Tracker. | N/A — if an issue surfaces here, restart from Stage 2 | Verbal approval is not sufficient. Written confirmation only.
REVISION POLICY
Rounds included:
What counts as a revision: | Corrects a factual error, missing required brand element, or FTC disclosure issue. Creator followed the brief — something wasn't right in the output.
What counts as a new request: | Brand changes creative direction, adds deliverables, or requests reshoots after the creator followed the agreed brief. Scoped and priced separately.
Creator turnaround on revisions:
If revision rounds are exhausted: | Marketing lead and creator align on scope before any additional work begins. Nothing goes back for another round without written agreement from both parties.
IF BRAND DOESN'T RESPOND
Creator follow-up timeline:
Default approval trigger: | If no response within [Y] days of initial submission, content is approved as submitted — unless a hold has been explicitly communicated in writing.
Note: | This clause protects both parties. The number goes in writing before kickoff, not after something goes sideways.
REGULATED INDUSTRY STAGES — Insert between Stage 3 and Stage 4 when applicable
Stage | Reviewer / Role | What They're Evaluating | Turnaround (Business Days) | Approval Signal | Revision Trigger | Notes / Escalation
Stage 3a — Medical / Legal / Financial Review |  | Regulatory claim review, required disclosures by jurisdiction, platform-specific compliance, industry body requirements |  | Written sign-off with compliance log reference number | Unsubstantiated efficacy claim, jurisdiction-specific language violation, missing mandated disclosure | This review starts at the brief stage, not the draft stage. If compliance hasn't seen the brief, the draft is starting wrong.
Stage 3b — Compliance Documentation Log | Campaign owner | Confirm all regulatory review documentation is filed and accessible | Same day approval is issued | Log entry created in [compliance system or folder path] | Missing documentation stops publish | Applies to all content types, including repurposed or reformatted assets from this campaign